## Sheet1
Sr.No | Task | Priority | Status | Start date | End date | Deliverable | Notes
1 | Set up project repository (GitHub, CI/CD, ReadTheDocs) | P0 | Not started | 2025-02-24 | 2025-03-22
2 | Define module structure (folders, core files, naming conventions) | P0 | Not started | 2025-02-28 | 2025-03-29
3 | Implement missing value handling (drop rows/columns, imputation strategies) | P0 | Not started | 2025-03-04 | 2025-04-05
4 | Develop categorical encoding methods (One-Hot, Label, Frequency encoding) | P0 | Not started | 2025-03-08 | 2025-04-12
5 | Implement scaling & normalization (MinMax, StandardScaler, RobustScaler) | P0 | Not started | 2025-03-12 | 2025-04-19
6 | Add outlier detection & removal (Z-score, IQR, Isolation Forest) | P0 | Not started | 2025-03-16 | 2025-04-26
7 | Feature selection methods (Variance threshold, correlation-based) | P0 | Not started | 2025-03-20 | 2025-05-03
8 | Automated decision nodes logic (preprocessing strategy selection based on dataset characteristics) | P0 | Not started | 2025-03-24 | 2025-05-10
9 | Optimize processing speed (vectorized operations, NumPy/Pandas optimizations) | P0 | Not started | 2025-03-28 | 2025-05-17
10 | Write unit tests (pytest coverage ≥ 80%) | P0 | Not started | 2025-04-01 | 2025-05-24
11 | Validate module on diverse datasets (small, large, imbalanced, noisy, etc.) | P0 | Not started | 2025-04-05 | 2025-05-31
12 | Create documentation & Jupyter Notebook tutorials | P0 | Not started | 2025-04-09 | 2025-06-07
13 | Write an interactive README with usage examples | P0 | Not started | 2025-04-13 | 2025-06-14
14 | Publish module on PyPI (preprocessx) and test pip install | P0 | Not started | 2025-04-17 | 2025-06-21
15 | Set up GitHub Actions for CI/CD & collect early user feedback | P0 | Not started | 2025-04-21 | 2025-06-28